## Product Backlog
PRODUCT BACKLOG
ID | ITEM | OWNER | PRIORITY | EFFORT | STATUS | DEFINITION OF DONE | NOTES
1 | Patient landing page | Patient | 8 | 4 | To Do | Given that I sign in, when I load into the website then the first page, I am present with is a landing page tailored to me as a patient. | Will welcome the patient to the system as well as provide links to frequently accessed pages that the patient has access to
2 | Doctor landing page | Doctor | 8 | 4 | To Do | Given that I sign in, when I load into the website then the first page, I am present with is a landing page tailored to me as a doctor. | Will welcome the doctor to the system as well as provide links to frequently accessed pages that a doctor has access to
3 | Super Administrator landing page | Super Administrator | 8 | 5 | To Do | Given that I sign in, when I load into the website then the first page, I am present with is a landing page tailored to me as a super administrator. | Will only welcome the super administrator, as they can access all controls available through the navigation menu
4 | Navigation bar tailored to the patient user type | Patient | 10 | 6 | To Do | Given that I am a patient, when I need to access my health info, view my calendar or have a chat with my doctor then I can access the appropriate pages for those tasks through the navigation bar. | Will include pages; health info, calendar, text chat
5 | Navigation bar tailored to the doctor user type | Doctor | 10 | 6 | To Do | Given that I am a doctor, when I need to edit my availabilities, view my patients, chat with my patients or access patient prescriptions, then I can access the appropriate pages for those tasks through the navigation bar. | Will include pages; availabilities, text chat, patient list, prescriptions
6 | Navigation bar tailored to the super admin user type | Super Administrator | 10 | 7 | To Do | Given that I am a super administrator, when I need to view users, view each user type’s point of view on the website whether it be a patient or doctor, edit users or create new users, then I can access the appropriate pages for those tasks through the navigation bar. | Will include pages; create user, view all users, edit users. In addition the super administrator can view all pages the doctor and patient users can view
7 | Edit Availability | Doctor | 8 | 8 | To Do | Given that I am a doctor, when I need to edit my availabilities, then I am able to tell the system which days and times I am available to work. | Will show current availability in a calendar like format.
8 | View Patient Health Info | Doctor | 10 | 5 | To Do | Given that I am a doctor, when I want to see my patients health information, then I am able to see that information by navigating to their page from the patients list | Will also have edit health info on this page
9 | Edit Patient Health Info | Doctor | 10 | 7 | To Do | Given that I am a doctor, when I want to edit my patients health information, then I am able to see and edit that information by navigating to their page from the patients list | Will also have view health info on this page
10 | View Health Info | Patient | 5 | 5 | To Do | Given that I am a patient, when I want to check my health records, then I am able to navigate to my health record page and see the relevant information. | Patients cannot edit their medical records, only their personal details
11 | Book an Appointment | Patient | 8 | 5 | To Do | Given that I am a patient, when I want to book an appoitment, then I am able to go to the website and look through the times available for each doctor. | Patient will be shown a list of times available for a doctor and will select from that list. Doctors do not need to confirm a booking.
12 | View Calendar | Doctor | 8 | 4 | To Do | Given that I am a doctor, when I want to view my schedule for a week, then I am able to see the appointments for that given week. | Doctors can select a date and that week will be shown.
13 | Edit Personal Details | Patient | 4 | 5 | To Do | Given that I am a patient, when I want to update my address, I am able to navigate to my health information page and edit it. | This will update patients details in the database.
14 | Main Page | All users | 10 | 4 | To Do | Given that I am a user whoever is doctor, patient or admin, when I want to learn more about Neighborhood Doctors and create an account or log in my account, then I am able to log in to the system or choose whether I should create an account. | Need to add the introduction about Neighborhood Doctors.
15 | Doctor Sign Up Page | Doctor | 10 | 5 | To Do | Given that I am a doctor, when I get a job in Neighborhood Doctors and am ready to make an account, then I am able to sign up with my email, password and doctor role or another services such as Google etc. | Will have a checking function whether this user is a doctor.
16 | Patient Sign Up Page | Patient | 10 | 5 | To Do | Given that I am a patient, when I feel sick and want to make an account in Neighborhood Doctors, then I am able to sign up with my email, password and patient role or another services such as Google etc. | No need to make a checking function for the patient role.
17 | Admin Sign Up Page | Admin | 10 | 5 | To Do | Given that I am an admin, when I get a job as a developer in Neighborhood Doctors and am ready to make an account, then I am able to sign up with my email, password and admin role or another services such as Google etc. | Will have a checking function whether this user is a admin.
18 | Doctor Log In Page | Doctor | 10 | 5 | To Do | Given that I am a doctor, when I prepare for working in Neighborhood Doctors, then I am able to log in with my email and password or another services such as Google etc. | Access the doctor information from the database.
19 | Patient Log In Page | Patient | 10 | 5 | To Do | Given that I am a patient, when I want to log in to Neighborhood Doctors,then I am able to log in with my email and password or another services such as Google etc. | Access the patient information from the database.
20 | Admin Log In Page | Admin | 10 | 5 | To Do | Given that I am an admin, when I am about to do the maintance job in Neighborhood Doctors, then I am able to log in with my email and password or another services such as Google etc. | Access the admin information from the database.
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #REF!
| Previous Year | #REF! | #REF!
| Position | #REF! | #REF! | #REF! | #REF! | #REF!
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | Patient landing page | #N/A | #N/A | #N/A | #N/A | #N/A
2 | Doctor landing page | #N/A | #N/A | #N/A | #N/A | #N/A
3 | Navigation bar tailored to the patient user type | #N/A | #N/A | #N/A | #N/A | #N/A
4 | Navigation bar tailored to the doctor user type | #N/A | #N/A | #N/A | #N/A | #N/A
5 | Navigation bar tailored to the super admin user type | #N/A | #N/A | #N/A | #N/A | #N/A
6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | Edit Availability | #N/A | #N/A | #N/A | #N/A | #N/A
8 | View Patient Health Info | #N/A | #N/A | #N/A | #N/A | #N/A
9 | Edit Patient Health Info | #N/A | #N/A | #N/A | #N/A | #N/A
10 | View Health Info | #N/A | #N/A | #N/A | #N/A | #N/A
11 | Book an Appointment | #N/A | #N/A | #N/A | #N/A | #N/A
12 | View Calendar | #N/A | #N/A | #N/A | #N/A | #N/A
13 | Edit Personal Details | #N/A | #N/A | #N/A | #N/A | #N/A
14 | Main Page | #N/A | #N/A | #N/A | #N/A | #N/A
15 | Doctor Sign Up Page | #N/A | #N/A | #N/A | #N/A | #N/A
16 | Patient Sign Up Page | #N/A | #N/A | #N/A | #N/A | #N/A
17 | Admin Sign Up Page | #N/A | #N/A | #N/A | #N/A | #N/A
18 | Doctor Log In Page | #N/A | #N/A | #N/A | #N/A | #N/A
19 | Patient Log In Page | #N/A | #N/A | #N/A | #N/A | #N/A
20 | Admin Log In Page | #N/A | #N/A | #N/A | #N/A | #N/A
21 |  | #N/A | #N/A | #N/A | #N/A | #N/A
22 |  | #N/A | #N/A | #N/A | #N/A | #N/A
23 |  | #N/A | #N/A | #N/A | #N/A | #N/A
24 |  | #N/A | #N/A | #N/A | #N/A | #N/A
25 |  | #N/A | #N/A | #N/A | #N/A | #N/A