## Product Backlog
PRODUCT BACKLOG
ID | ITEM | OWNER | PRIORITY | EFFORT | STATUS | DEFINITION OF DONE | NOTES
1 | Patient landing page | Patient | 8 | 4 | To Do | Given that I sign in, when I load into the website then the first page, I am present with is a landing page tailored to me as a patient. | Will welcome the patient to the system as well as provide links to frequently accessed pages that the patient has access to
2 | Doctor landing page | Doctor | 8 | 4 | To Do | Given that I sign in, when I load into the website then the first page, I am present with is a landing page tailored to me as a doctor. | Will welcome the doctor to the system as well as provide links to frequently accessed pages that a doctor has access to
3 | Super Administrator landing page | Super Administrator | 8 | 5 | To Do | Given that I sign in, when I load into the website then the first page, I am present with is a landing page tailored to me as a super administrator. | Will only welcome the super administrator, as they can access all controls available through the navigation menu
4 | Navigation bar tailored to the patient user type | Patient | 10 | 6 | To Do | Given that I am a patient, when I need to access my health info, view my calendar or have a chat with my doctor then I can access the appropriate pages for those tasks through the navigation bar. | Will include pages; health info, calendar, text chat
5 | Navigation bar tailored to the doctor user type | Doctor | 10 | 6 | To Do | Given that I am a doctor, when I need to edit my availabilities, view my patients, chat with my patients or access patient prescriptions, then I can access the appropriate pages for those tasks through the navigation bar. | Will include pages; availabilities, text chat, patient list, prescriptions
6 | Navigation bar tailored to the super admin user type | Super Administrator | 10 | 7 | To Do | Given that I am a super administrator, when I need to view users, view each user type’s point of view on the website whether it be a patient or doctor, edit users or create new users, then I can access the appropriate pages for those tasks through the navigation bar. | Will include pages; create user, view all users, edit users. In addition the super administrator can view all pages the doctor and patient users can view
7 | Edit Availability | Doctor | 8 | 8 | To Do | Given that I am a doctor, when I need to edit my availabilities, then I am able to tell the system which days and times I am available to work. | Will show current availability in a calendar like format.
8 | View Patient Health Info | Doctor | 10 | 5 | To Do | Given that I am a doctor, when I want to see my patients health information, then I am able to see that information by navigating to their page from the patients list | Will also have edit health info on this page
9 | Edit Patient Health Info | Doctor | 10 | 7 | To Do | Given that I am a doctor, when I want to edit my patients health information, then I am able to see and edit that information by navigating to their page from the patients list | Will also have view health info on this page
10 | View Health Info | Patient | 5 | 5 | To Do | Given that I am a patient, when I want to check my health records, then I am able to navigate to my health record page and see the relevant information. | Patients cannot edit their medical records, only their personal details
11 | Book an Appointment | Patient | 8 | 5 | To Do | Given that I am a patient, when I want to book an appoitment, then I am able to go to the website and look through the times available for each doctor. | Patient will be shown a list of times available for a doctor and will select from that list. Doctors do not need to confirm a booking.
12 | View Calendar | Doctor | 8 | 4 | To Do | Given that I am a doctor, when I want to view my schedule for a week, then I am able to see the appointments for that given week. | Doctors can select a date and that week will be shown.
13 | Edit Personal Details | Patient | 4 | 5 | To Do | Given that I am a patient, when I want to update my address, I am able to navigate to my health information page and edit it. | This will update patients details in the database.
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #REF!
| Previous Year | #REF! | #REF!
| Position | #REF! | #REF! | #REF! | #REF! | #REF!
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | Patient landing page | #N/A | #N/A | #N/A | #N/A | #N/A
2 | Doctor landing page | #N/A | #N/A | #N/A | #N/A | #N/A
3 | Navigation bar tailored to the patient user type | #N/A | #N/A | #N/A | #N/A | #N/A
4 | Navigation bar tailored to the doctor user type | #N/A | #N/A | #N/A | #N/A | #N/A
5 | Navigation bar tailored to the super admin user type | #N/A | #N/A | #N/A | #N/A | #N/A
6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | Edit Availability | #N/A | #N/A | #N/A | #N/A | #N/A
8 | View Patient Health Info | #N/A | #N/A | #N/A | #N/A | #N/A
9 | Edit Patient Health Info | #N/A | #N/A | #N/A | #N/A | #N/A
10 | View Health Info | #N/A | #N/A | #N/A | #N/A | #N/A
11 | Book an Appointment | #N/A | #N/A | #N/A | #N/A | #N/A
12 | View Calendar | #N/A | #N/A | #N/A | #N/A | #N/A
13 | Edit Personal Details | #N/A | #N/A | #N/A | #N/A | #N/A
14 |  | #N/A | #N/A | #N/A | #N/A | #N/A
15 |  | #N/A | #N/A | #N/A | #N/A | #N/A
16 |  | #N/A | #N/A | #N/A | #N/A | #N/A
17 |  | #N/A | #N/A | #N/A | #N/A | #N/A
18 |  | #N/A | #N/A | #N/A | #N/A | #N/A
19 |  | #N/A | #N/A | #N/A | #N/A | #N/A
20 |  | #N/A | #N/A | #N/A | #N/A | #N/A
21 |  | #N/A | #N/A | #N/A | #N/A | #N/A
22 |  | #N/A | #N/A | #N/A | #N/A | #N/A
23 |  | #N/A | #N/A | #N/A | #N/A | #N/A
24 |  | #N/A | #N/A | #N/A | #N/A | #N/A
25 |  | #N/A | #N/A | #N/A | #N/A | #N/A