## Product Backlog
PRODUCT BACKLOG
ID | ITEM | OWNER | PRIORITY | EFFORT | STATUS | DEFINITION OF DONE | NOTES
1 | Patient landing page | Patient | 8 | 4 | To Do | Given that I sign in, when I load into the website then the first page, I am present with is a landing page tailored to me as a patient. | Will welcome the patient to the system as well as provide links to frequently accessed pages that the patient has access to
2 | Doctor landing page | Doctor | 8 | 4 | To Do | Given that I sign in, when I load into the website then the first page, I am present with is a landing page tailored to me as a doctor. | Will welcome the doctor to the system as well as provide links to frequently accessed pages that a doctor has access to
3 | Super Administrator landing page | Super Administrator | 8 | 5 | To Do | Given that I sign in, when I load into the website then the first page, I am present with is a landing page tailored to me as a super administrator. | Will only welcome the super administrator, as they can access all controls available through the navigation menu
4 | Navigation bar tailored to the patient user type | Patient | 10 | 6 | To Do | Given that I am a patient, when I need to access my health info, view my calendar or have a chat with my doctor then I can access the appropriate pages for those tasks through the navigation bar. | Will include pages; health info, calendar, text chat
5 | Navigation bar tailored to the doctor user type | Doctor | 10 | 6 | To Do | Given that I am a doctor, when I need to edit my availabilities, view my patients, chat with my patients or access patient prescriptions, then I can access the appropriate pages for those tasks through the navigation bar. | Will include pages; availabilities, text chat, patient list, prescriptions
6 | Navigation bar tailored to the super admin user type | Super Administrator | 10 | 7 | To Do | Given that I am a super administrator, when I need to view users, view each user type’s point of view on the website whether it be a patient or doctor, edit users or create new users, then I can access the appropriate pages for those tasks through the navigation bar. | Will include pages; create user, view all users, edit users. In addition the super administrator can view all pages the doctor and patient users can view
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #REF!
| Previous Year | #REF! | #REF!
| Position | #REF! | #REF! | #REF! | #REF! | #REF!
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | Patient landing page | #N/A | #N/A | #N/A | #N/A | #N/A
2 | Doctor landing page | #N/A | #N/A | #N/A | #N/A | #N/A
3 | Navigation bar tailored to the patient user type | #N/A | #N/A | #N/A | #N/A | #N/A
4 | Navigation bar tailored to the doctor user type | #N/A | #N/A | #N/A | #N/A | #N/A
5 | Navigation bar tailored to the super admin user type | #N/A | #N/A | #N/A | #N/A | #N/A
6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 |  | #N/A | #N/A | #N/A | #N/A | #N/A
8 |  | #N/A | #N/A | #N/A | #N/A | #N/A
9 |  | #N/A | #N/A | #N/A | #N/A | #N/A
10 |  | #N/A | #N/A | #N/A | #N/A | #N/A
11 |  | #N/A | #N/A | #N/A | #N/A | #N/A
12 |  | #N/A | #N/A | #N/A | #N/A | #N/A
13 |  | #N/A | #N/A | #N/A | #N/A | #N/A
14 |  | #N/A | #N/A | #N/A | #N/A | #N/A
15 |  | #N/A | #N/A | #N/A | #N/A | #N/A
16 |  | #N/A | #N/A | #N/A | #N/A | #N/A
17 |  | #N/A | #N/A | #N/A | #N/A | #N/A
18 |  | #N/A | #N/A | #N/A | #N/A | #N/A
19 |  | #N/A | #N/A | #N/A | #N/A | #N/A
20 |  | #N/A | #N/A | #N/A | #N/A | #N/A
21 |  | #N/A | #N/A | #N/A | #N/A | #N/A
22 |  | #N/A | #N/A | #N/A | #N/A | #N/A
23 |  | #N/A | #N/A | #N/A | #N/A | #N/A
24 |  | #N/A | #N/A | #N/A | #N/A | #N/A
25 |  | #N/A | #N/A | #N/A | #N/A | #N/A